## Testing 0707
Issue | Description | Example |  | Dev Remarks | Exp Completion date | Dev Assignee | Dev Status | Status | Required Doc
Customer Categories |  |  |  | need discussion | 2025-07-10 |  | in progress | Need to discuss with sanjana
Brand page | Show Filters for Product Name, Category |  |  |  | 2025-07-10 |  | in progress | Discussed
Brand page | Shop by Category < Electrical < ABB [Product Count Ef. 1142], when I click show 3743 i.e. All products in ABB Ideal: On Click to ABB, Show all ABB, Filter Applied for Electrical Category |  |  |  | 2025-07-09 |  | in progress | Discussed
Products List | Current, default show 2 rows, extend to 5 rows in result i.e. 5x5 = 25 Products | https://connect.procmart.com/shop-by-brand-name/2361?brandName=Jainson |  |  | 2025-07-09 |  | in progress | Discussed
Product Details | When Idem is added to cart, if add to cart button is pressed twice, then 2 qty gets added, if thrice, then nothing happens Ideal: Default Qty should be Null, In qty Selector, it should be selected, then only Add to Cart should be visible |  |  |  | 2025-07-09 |  | in progress | Discussed
Product Details | Image Size to be fixed |  | Dhiraj Gogoi | already image size is fixed let me know if there any fixed parameters will update accordingly - need padding in px |  | shubham | input required | Design Reqd
Product Details | Frequently Bought Together is missed |  |  | need to check data |  |  | pending | Discussed
Wishlist | Wishlist feature is not working |  | Dhiraj Gogoi | needed a discussion |  |  | input required | Design Reqd
Common Navigation | User Email if greater than 20 characters, then show it truncated i.e. '...' at the end |  |  | for email and name | 2025-07-09 | shubham | in progress | Discussed
Product List/ Details | If Product Image is not available, show Brand Image |  |  | is this a common feature on every page where we display products and let us know what needs to be displayed if the brand image is not available - need placeholder image - to be provided by dhiraj |  | shubham | input required | Discussed
Product Details | Add ProcMart Material ID |  |  | where should we add this. please define the placement |  |  | input required | Design Reqd
Product Details | Make Brand in the table as Hyperlink |  |  |  | 2025-07-09 |  | in progress | Discussed
Product List | In Filters, remove the keyword 'Select' e.g. No 'Select Variant' show just 'Variant'. Caps Small/Proper Noun |  |  |  | 2025-07-09 | shubham | in progress | Discussed
Product List | Brand Filter is not visible |  |  |  | 2025-07-10 |  | in progress
Product List | Brand Filter is not visible | https://connect.procmart.com/shop-by-category/7&category_name=FASTENERS |  | same as point 15 |  |  | in progress
Product Details | Brand Name and few other details i.e. Abbrevations should be shown in Capital Letter like on Product List Pages | https://connect.procmart.com/products/335141 |  |  |  | shubham | in progress
Product Details | Part No/ Other missing details should not be shown in Table if not available (Unstructured) | https://connect.procmart.com/products/335141 |  |  | 2025-07-10 |  | in progress
Brand Page | Show banners as per shared list status against each brand | https://docs.google.com/spreadsheets/d/1AALHgZ8DHFgFVTBfumTYziNXPPQOuPJA7YE9SRf2xm4/edit?usp=sharing |  | we have already share the upload sheet structure. please follow that. reshare the sheet with correct format |  | jayanth | input required | Discussed
Footer | Shop by Brands < Should be redirected to https://connect.procmart.com/shop-by-brand |  |  |  | 2025-07-09 |  | in progress
Footer | Remove Support Portal Option |  |  |  | 2025-07-09 | shubham | in progress
Cart | Delivery Period Incorrect in Cart/ Default showing as 3-5 days |  |  |  | 2025-07-09 |  | done
Product Details | Breadcrumbs are missing |  |  | we already discussed on this. the issue is with structured and unstructured. how to display both? share the design for both the versions |  |  | input required
Search | Priority Hierarchy Level Search E.g. Cable, Motor etc 1. Product Name 2. Brand 3. Internal Specification / Parameters 4. Client Specification |  |  | this is done. plz share the creteria for testing search results (100% accuracy) with examples. so that we can develop accordingly | 2025-07-08 |  | deployed | Pending Prod
Search | If Brand Name explicity is typed, redirect them to that Brand Page |  |  | please share all the search requirements at a time so that we design architechure accordingly. | 2025-07-11 |  | in progress | Discussed
Search | Basic Typos are not supported e.g, Bering |  |  | this is done. plz share the creteria for testing search results (100% accuracy) with examples. so that we can develop accordingly |  |  | deployed
Filter | View All Filters, 1st Parameter should be shown expanded by default |  |  | need clarity - share the expected design |  |  | in progress
Filter | View All Filters, Nothing Happening on clicking on 'View' Button |  |  | need clarity on the functionality |  |  | in progress
Filters | Small Cards for Applied Filters. E.g. Variant Name |  |  | small cards means ?? |  |  | in progress | Design Link updated | https://www.figma.com/design/kmLvZp3UtoynmGwZ50LtFN/Catalogue-E-com?node-id=1843-2709&t=jwq1pEwZCdlk2u2X-1 In the filter tag page
Product List | If Products are added to cart, toaster should come/ Success Message |  |  |  | 2025-07-09 |  | in progress
Common Navigation/ Login | Case to be changed for Tagline 'Keeps Machines Running' |  |  | plz share the logo image |  | shubham | input required | Design need
Home | Top Browsed Products, Should have Product Name | https://connect.procmart.com/ |  |  | 2025-07-10 |  | in progress
Product List < Category < Previously Bought | Redundant Tags are getting added - Your Choice | https://connect.procmart.com/shop-by-category/6 |  |  | 2025-07-11 |  | in progress
Product Card | Tags: Previously Bought, Frequently Ordered Should be consistent on the whole website, not just sections Previously Bought: active status materialId exists in buyerPOItem table for the client Frequently Ordered: active materialId exists in buyerInvoiceItem table for more than 5 times in last 6 months |  |  |  | 2025-07-11 |  | in progress
Browsed/ Data Structure | Save the browing history/ searched keywords. Browsing History to be saved, and showed to the user in Search Bar |  |  | we are already storing the search history and displaying. please clearley mention what else needed with a clear example |  |  | phase 2 | Discussed | Ongoing process
Login | Google Sign On+ MS Login Functionality is not working If it would take time, so hide it |  |  | waiting for approval will hide it | 2025-07-09 | shubham | in progress
Login | Remove 'New to PROCMART? Request access' |  |  |  | 2025-07-09 | shubham | in progress
Login | Left Structure to be changed, design to shared by 08-07 EOD |  | Dhiraj Gogoi | will update the timeline once the design is shared |  |  | input required
Brands | Polycab is not showing in the Top Brands for Electrical, not even on View All | https://connect.procmart.com/shop-by-brand-and-category/Electrical |  | need to check the data |  |  | pending
Quick Filter Drop Down | In the quick filter dropdown, the list is technically scrollable, but it doesn’t visually indicate scrollability. Can we add a visual cue for scrollability (e.g., scrollbar, fade at the bottom, or a “+ more options” indicator). |  |  | need discussion |  | shubham | in progress
Cart page | Whenever we remove an item from the card, the content of the toaster needs to be changed. Instead of showing "WARNING YOUR CART IS EMPTY" it should have a content showing (1 ITEM REMOVED FROM THE CART) |  |  | we have already removed the toast few days back. |  | shubham | in progress | Discussed
Quick Filter Drop Down | When a filter is selected from the quick filter dropdown, the page jumps or shifts down, disrupting the user’s focus and breaking the visual continuity especially when filters are selected from the middle of the page. Instead the product results should update without shifting the filter section's position. |  |  |  | 2025-07-10 | shubham | in progress
Category Search | In the catgeory drop down of the search bar, need to show a drop down pointer to make the category section seems like unscrolable |  |  | already developed | 2025-07-08 | shubham | in progress
Filter Tags | Filters should have deselect Option at filters tag only instead of clear all |  |  | clear filters were kept beacuse its not shown on figma. please share the figma design for this |  |  | in progress
Common Navigation | New Navigation Colour/ UI to shared by tomorrow EOD |  | Dhiraj Gogoi | will update time line once design is shared |  |  | input required
Category Section | In the home page category section( eg: Electrical, Fastners, mechanical etc) font weight should be medium. | https://connect.procmart.com |  | need discussion |  | shubham | in progress
Cart < Address | Billing Address is always showing 'Undefined', bottom right section |  |  |  | 2025-07-10 |  | in progress
Horizontal Product Card | In the Horz product card ERP tag should be removed, and the product title font should match the styling used in vertical cards | https://connect.procmart.com/shop-by-category/6 |  | epr code should be entirely removed or only remove if its not present ? | 2025-07-10 | shubham | in progress
Cart | Error on clicking Final 'Continue' Button | https://drive.google.com/file/d/1RfrehpQU6SxI_3jepQjaVkIHv6VDlLSf/view?usp=sharing |  | we are updating the backend. if there is a trigger at the time of update it will throw an error |  |  | in progress | Portal issue | no issue on portal - testing done at at which server apis is under maintanance witl raise errors
Cart < Address | User should be able to see Billing and Shipping Address, associated to their Branch only |  |  | need to check data |  |  | in progress
Quotation | Download Quotation Name should be Document No |  |  |  | 2025-07-09 |  | done
Quotation | Quotation Valid Upto : ' is blank Ideal: 30 Days |  |  | need to check data |  |  | in progress | Portal Issue
Cart < Address | Billing Address Title showing Blank for e,g, Sonipat, Delhi etc Y-65 Hauz Khas Pincode: 110016 GSTIN: 07AAACC3269J1ZM |  |  | repeated point - 47 |  |  | in progress
Product Description page | Need to change the product description page background to white, as given in figma | https://drive.google.com/file/d/1qxKqlSf27T_s-UmCUNUaruqgfuLnyA62/view?usp=share_link |  | issue as discuused previuosly - the background of the images are usually white and if the image section background is changed to grey it will look odd |  | shubham | in progress
Footer | LinkedIn - https://www.linkedin.com/company/procmart Wikipedia -https://en.wikipedia.org/wiki/ProcMart Change Icon from X to Wikipedia |  |  |  | 2025-07-09 | shubham | in progress
Home < Top Browsed | Page shows blank sometimes - https://connect.procmart.com/search-by-product/VALVE?category_id=12&category_name=Hydraulics%20&%20Pneumatics | https://connect.procmart.com/search-by-product/VALVE?category_id=12&category_name=Hydraulics%20&%20Pneumatics |  |  | 2025-07-10 |  | in progress
materialMasterTemp | Allow productSpecificationJSON in temp table so we can work on making structure for temp material IDs too |  |  | need discussion |  |  | in progress
Product Details, Cart | Replace Rs. Icon with ₹, to keep it consistent |  |  |  | 2025-07-10 | shubham | in progress
Footer Support section | The padding in the 'Support' section of the footer is misaligned. | https://connect.procmart.com |  |  | 2025-07-11 | shubham | in progress
Category Drop Down menu | When hovering over the Category or product dropdown (mega menu), if the cursor stays inside the dropdown area and the user scrolls, the dropdown moves along with the page, rather than staying fixed or closing. | https://connect.procmart.com |  |  | 2025-07-11 |  | in progress
Data | If any, share the list of Product Names and Material IDs if Image is not present |  |  | need discussion

## Sheet1
Date | Page | Description | Link | Type | Dev Status | Dev Remark | Prod Remark | Retest Status
2025-06-28 | Reorder | Reorder Page Not Working | https://client.procmart.com/ | Bug | Closed | not in plan design not shared | Needs to removed |  | prodcut
2025-06-28 | Track Order | It sould be eirther blank or have tracking data right now it is redirecting to home page | https://client.procmart.com/Track-Order | Bug | Closed | not in plan design not shared | Needs to be removed |  | product
2025-06-28 | Request a quote | Page not Working | https://client.procmart.com/ | Bug | Closed | redirect to cart page |  |  | Product
2025-06-28 | Shop By brand | Every Brand Page has Usha Logo | https://client.procmart.com/shop-by-brand-name/1740?categoryId=6 | Styling | Pending | hard coaded banner. as banner images were not shared yet | https://docs.google.com/spreadsheets/d/1AALHgZ8DHFgFVTBfumTYziNXPPQOuPJA7YE9SRf2xm4/edit?usp=sharing
2025-06-28 | Shop By brand | Shop by brand Front Page Missing Logos of Brand in first two cards | https://client.procmart.com/shop-by-brand | Styling | Pending | those brand logos not shared | Logo are uploaded https://docs.google.com/spreadsheets/d/145iv9g3FLlwBviSKvoV51Mg_FRqUtWf_2HQcY8edM08/edit?usp=sharing
2025-06-28 | Shop By brand | Extensive surfing on this page making it blank | https://client.procmart.com/shop-by-brand | Bug | Closed | should be resolved by jun 30 morning. on 28 data is not updated
2025-06-28 | Home Page | Links Added to footer are redirecting to home page | https://client.procmart.com/ | Bug | Closed | working on it but we dont info for al
2025-06-28 | Shop by Category | Category Page Going Blank | https://client.procmart.com/shop-by-category/6 | Bug | Closed | data issues |  |  |  |  | bearing | ball bearing 0.5 | json
2025-06-28 | Cart | Cart is not having product details like UOM, HSN and ERP Code | https://client.procmart.com/cart | Display Info | Closed | will add |  |  |  | materialId / client erp |  | box bearing | json
2025-06-28 | Cart | Delivery Stated in Front page is 14 Days but at cart it shows 4 days | https://client.procmart.com/cart | Display Info | Closed |  |  |  | Row 10
2025-06-30 | Subcategory Drop Down | The subcategory names are written in an inconsistent way, some are in ALL CAPS (like "INDUCTION MOTOR"), while others use only the first letter capitalized (like "Pin" or "Ring").Use either Sentence case or Title Case | https://drive.google.com/file/d/1hjjnQBVjore67GoT5Pn2DosigxIcvS96/view?usp=sharing | UI/UX issues | Closed | displayed as it is from database. will modify to title case | [5 empty] | bearing 0.5mm
2025-06-30 | Subcategory Drop down Hover | In the subcategory hover container, the header are breaking into multiple lines, causing layout misalignment and inconsistency.Can we have a display: flex for the hover container | https://drive.google.com/file/d/1hjjnQBVjore67GoT5Pn2DosigxIcvS96/view?usp=sharing | UI/UX issues | Closed | issue with flex is it takes container width which dirupts the display
2025-06-30 | Main Category Change | The categories in the search and homepage, should be as per client's custom categories |  | Data Issues | Discussion Required |  |  |  | Phase 2
2025-06-30 | Subcategory Drop Down | In the dropdown menu (e.g., under "Cable Lugs", "Lugs", "Motor"), the variable names like "PIN", "RING", "INDUCTION", etc., are are not clickable. | https://drive.google.com/file/d/1hjjnQBVjore67GoT5Pn2DosigxIcvS96/view?usp=sharing | UI/UX issues | Closed |  |  |  | will be redirected to product page
2025-06-30 | Electrical Subcategory/ All subcategory | The naming format of subcategory variables of all categoires is inconsistent. Use either Sentence case or Title Case | https://client.procmart.com/shop-by-category/6 | UI/UX issues | Closed | displayed as it is from database. will modify
2025-06-30 | Product | ERP Code should be hidden if Not Available, not "N/A" | https://client.procmart.com/products/316228 | UI/UX issues | Closed | fixed in product details page
2025-06-30 | Product | Wrong image mapping in Mechanical Category | https://client.procmart.com/shop-by-category/20 | Display Info |  | category image not found | Category Image are uploaded https://docs.google.com/spreadsheets/d/1WHY7mljl3dBjmR7C-AZsqnkDWzALSv1F-AlWOl_Qsf8/edit?usp=sharing |  | Product
2025-06-30 | Product | Product Search engine is not working for Windows |  | Display Info | Closed | browser compatibility issue - resolved
2025-06-30 | Product | Wrong Brand logo/Image (TVS) | https://client.procmart.com/shop-by-brand | Display Info |  | its a data issue. mapped the same from shared excel sheet
2025-06-30 | Product | Incorrect Title Font | https://client.procmart.com/products/439642 | Display Info |  | NA |  |  | Kalyan
2025-06-30 | Product | Product Title (Short text) & Product specifications (Long text) are same mentioned | https://client.procmart.com/products/297066 | Display Info | Closed | kept as a place holder as description is not available
2025-06-30 | Product | GST RATE (%) is not part of specifications | https://client.procmart.com/products/284034 | UI/UX issues | input required | NA
2025-06-30 | Product | Seperation line is missing in bottom of the Specifications | https://client.procmart.com/products/284026 | UI/UX issues | input required
2025-06-30 | Product | Category hirerchy Hyperlink is missing in product Page | https://client.procmart.com/products/284029 | UI/UX issues | Closed | need to discuss |  |  | Product
2025-06-30 | Product Card | Inconsistent Naming Format in Product Titles. Some are in Upper caps and lower caps. Use "Title Case" as given in figma across all pridct titles | https://client.procmart.com/shop-by-category/10 | UI/UX issues | Closed
2025-06-30 | Product Card | Product title is in regular font not according to the figma design. Use medium as font weight as given in figma | https://client.procmart.com/shop-by-category/10 | UI/UX issues | Closed
2025-06-30 | Product | Incorrect Products are mapped in IT Category | https://client.procmart.com/shop-by-category/16 | Material Codification
2025-06-30 | Product | Incorrect Search Results in Product Page | https://client.procmart.com/search-by-product/Ceiling%20Fan | Display Info | Closed | use url https://client.procmart.com/search-by-product/FAN?category_id=16&category_name=I.%20T.&variants=CEILING
2025-06-30 | Side Filters Drawer | Spacing between the filter list. Check figma for refernce | https://client.procmart.com/shop-by-brand-and-category/Electrical | UI/UX issues | Closed
2025-06-30 | Side Filters Drawer | When a filter (e.g., “Price Range”) is selected or focused, it currently shows a default blue outline (browser focus style),this should be replaced with an underline on the filter text to indicate selection | https://client.procmart.com/shop-by-brand-and-category/Electrical | UI/UX issues | Closed
2025-06-30 | Side Filters Drawer | The side filter panel currently allows horizontal scrolling, which can break the layout.Restrict horizontal scrolling within the side filter panel. | https://client.procmart.com/shop-by-brand-and-category/Electrical | UI/UX issues | Closed | its due to an extra experimental feature (price range) - removed now
2025-06-30 | Brand Logo Card | The stroke (border) color of the brand logo card does not match the defined style in Figma. | https://client.procmart.com/shop-by-brand-and-category/Electrical | UI/UX issues | Closed | pls attach screenshot of related one
2025-06-30 | Product Description Page | In the proudct description page, about product table doesnt align with figma design | https://client.procmart.com/products/279713 | UI/UX issues | Closed
2025-06-30 | Product Description Page | The background color of the entire page and product container on the PDP does not match the Figma design. | https://client.procmart.com/products/279713 | UI/UX issues | Closed | issue is with product images background (mostly the image backgrounds provided are in which which dont align with our design)
2025-06-30 | Product Description Page | The "Frequently Bought Together" section is missing in the developed PDP (Product Detail Page), | https://www.figma.com/design/kmLvZp3UtoynmGwZ50LtFN/Catalogue-E-com?node-id=821-3560&t=sq6ci7kQCGBAhgss-1 | UI/UX issues |  | data not available
2025-06-30 | Search Field | When a user selects a category (e.g., “Electrical”) in the search dropdown and begins typing, the search suggestions still show top-level categories (like “Fasteners,” “Bearings,” etc.) instead should show relevant products from the selected category. | https://client.procmart.com/search?text=Hex%20bearing | UI/UX issues | Closed
2025-06-30 | Home Page | In the home page, the picture is same for both Electrical and Mechanical |  | Content Issue | input required | relevent iamge is not shared | Category Image are uploaded https://docs.google.com/spreadsheets/d/1WHY7mljl3dBjmR7C-AZsqnkDWzALSv1F-AlWOl_Qsf8/edit?usp=sharing
2025-06-30 | Shop By brand | In shop by brand page, popular brand section is missing | https://client.procmart.com/shop-by-brand | UI/UX issues | Discussion Required | logic not clear | Top browsed Brands by client/ or display brands of top ordering products
2025-06-30 | Product Card | There is a visual inconsistency in the product cards where products without an image appear differently causing misalignment across the grid. | https://drive.google.com/file/d/1fZrAIV3HZ0DKexN6h67U4a7mXW9Z6XOn/view?usp=sharing | UI/UX issues | Closed
2025-06-30 | Button in Product Description page | The "Add to Cart" button and the quantity selector button have different border radii | https://client.procmart.com/products/284578 | UI/UX issues | Closed
2025-06-30 | Add to cart interaction | Currently, when a user clicks "Add to Cart", there is no visual feedback confirming the action. Need to display a toaster notification immediately after the "Add to Cart" button is clicked. | https://drive.google.com/file/d/19cUZ2Jxpud52a_ead45IIqtCjeHPShNU/view?usp=sharing | UI/UX issues | Closed | added toast
2025-06-30 | Home Page | On the homepage, sections like Electrical, Fasteners, and Mechanical currently have the same background color.Each of these sections should have a distinct background color as defined in the Figma design. | https://client.procmart.com | UI/UX issues | Closed
2025-06-30 | Home Page | On the homepage, the "View All" button under the Shop by Brand section is currently not functional | https://client.procmart.com | Bug | Closed
2025-06-30 | Brand Card | In the brand cards, the header (brand name) and subhead (category) follow inconsistent naming formats | https://client.procmart.com/shop-by-brand-and-category/Hydraulics%20%26%20Pneumatics | UI/UX issues | Closed
2025-07-01 | Logo Tagline | Need to change the tagline to " Keeps machines running" | https://client.procmart.com | Content Issue | input required | changed on login page for header need logo image
2025-07-01 | Domain Name | Need to change the domain to "connect.procmart.com" |  |  | Closed | now accessible via connect.procmart.com
2025-07-01 | Filter side drawer | In the filter side drawer of the product listing page, View all and clear button should be stikcy at the bottom of the drawer | https://client.procmart.com/search-by-product/NUT?category_id=7 | UI/UX issues | Closed
2025-07-01 | Circuit breaker Subcategory | Pages is not visible in mac laptops | https://client.procmart.com/search-by-product/CIRCUIT%20BREAKER?category_id=6 | Bug | Closed | browser issues resolved
2025-07-01 | Nut Product Card | Display name in the NUT section product card differs when we browse from shop by brand and when we | https://client.procmart.com/search-by-product/NUT?category_id=7 https://client.procmart.com/shop-by-brand-name/1193?categoryId=7&brandName=Apl&categoryName=Fasteners | Bug | Closed | displaying short desc
2025-07-01 | New User Banner | If exsisting user start shopping banner should be removed | https://client.procmart.com/shop-by-category/6 |  | Closed
2025-07-01 | Top Browsed | How the data is fetch for top Browsed
2025-07-01 | Search | Dropdown of search is not visible on some pages, e.g. if no product found, then dropdown doesn't show |  |  | Discussion Required
2025-07-01 | Product Filters | Brand filters not showing | https://client.procmart.com/search-by-product/BEARING |  | Closed | url is incorrect use https://client.procmart.com/search-by-product/BEARING?category_id=3&category_name=BEARINGS
2025-07-01 | Category | Brand Filters should be visible | https://client.procmart.com/shop-by-category/20 |  | Work in Progress
2025-07-01 | Category Brands | In the bottom after Page Nos. Brands are not showing | https://client.procmart.com/search-by-product/BEARING |  |  | https://client.procmart.com/search-by-product/BEARING?category_id=3&category_name=Bearings
2025-07-01 | Footer | Need to add a sepeartor line in the footer, to seperate it out from other sections |  | Styling | Closed | i have added pls check once
2025-07-01 | Product Image | Share pending product images to be shared |  |  |  | query shared to sanjana
2025-07-01 | Home Page | Picture is same for mechanical & electrical icon on homepage |  |  |  | need relevent image urls
2025-07-02 | Content | Calculation is wrong (82% on Lugs, the net price is wrong) | https://client.procmart.com/shop-by-category/6 | Content Issue | Discussion Required
2025-07-02 | Content | Polycab missing as top brand for electrical items | https://client.procmart.com/shop-by-category/6 | Content Issue
2025-07-02 | Category page | No photos are visible in the top row | https://client.procmart.com/shop-by-category/6 | Data Issues
2025-07-02 | Header | Header should be sticky. |  |  | Closed
2025-07-02 | Search | The image of the categories are not correct in the search drop down container | https://client.procmart.com/search?text=bearing | UI/UX issues | Closed
2025-07-02 | Toaster | When a user clicks on add to cart button in the product card, the toaster is not visible |  | UI/UX issues | Closed
2025-07-02 | Quick Filter Tags | Need to increase the spacing between the quick filter tags and the corresponding dropdown filter panels | https://client.procmart.com/search-by-product/SPARE%20PART?category_id=20&page=2&category_name=Mechanical | UI/UX issues | Closed
2025-07-02 | Product card Tags | For structured/permanent material IDs, the product card currently displays the “Brand” tag, which is redundant since the brand name is already part of the product title.Instead, show more relevant and informative attributes such as Material Grade, Type, or Specification, depending on the product category. | https://client.procmart.com/shop-by-category/20 | Display Info | Closed
2025-07-02 | Product card Tags | For unstructured material IDs, it's acceptable to continue showing the Brand tag alongside other basic info if available. | https://client.procmart.com/shop-by-category/7 | Display Info | Closed
2025-07-02 | Banner | The subcategory strip and banner spacing are not adapting well to the content height. When subcategory names wrap into two lines, the layout becomes visually compact and cramped | https://client.procmart.com/shop-by-category/12 | UI/UX issues | Closed
2025-07-02 | Quick Filter Drop Down | In the quick filter dropdown, the list is technically scrollable, but it doesn’t visually indicate scrollability. Can we add a visual cue for scrollability (e.g., scrollbar, fade at the bottom, or a “+ more options” indicator). | https://client.procmart.com/search-by-product/GEARBOX?category_id=20&category_name=Mechanical | UI/UX issues | input required
2025-07-02 | Cart Page | Spacing between the quanitty selector and pricing need to be increased | https://client.procmart.com/cart | UI/UX issues | Closed
2025-07-02 | Cart Page | In the order summary container, the order summary header has a container box that should be removed | https://client.procmart.com/cart | UI/UX issues | Closed
2025-07-02 | Cart page | Whenever we remove an item from the card, the content of the toaster needs to be changed. Instead of showing "WARNING YOUR CART IS EMPTY" it should have a content showing (1 ITEM REMOVED FROM THE CART) | https://client.procmart.com/cart | Content Issue | Closed
2025-07-02 | Delivery Status | Delivery Status is not dynamic |  | Bug | input required
2025-07-02 | Quick Filter Drop Down | When a filter is selected from the quick filter dropdown, the page jumps or shifts down, disrupting the user’s focus and breaking the visual continuity especially when filters are selected from the middle of the page. Instead the product results should update without shifting the filter section's position. | https://client.procmart.com/search-by-product/LUGS?category_id=6&category_name=Electrical&variants=PIN&SIZE=2.5 | UI/UX issues | Pending
2025-07-02 | Shop by brand- Electrical or any category | The filter tags (e.g., All Filters, Select Brand) are currently placed above the "ELECTRICAL PRODUCTS" section header. Instead it should be relocated below the "ELECTRICAL PRODUCTS" header. | https://client.procmart.com/shop-by-brand-and-category/Electrical | UI/UX issues | Closed
2025-07-02 | Serach Bar | In the catgeory drop down of the search bar, need to show a drop down pointer to make the category section seems like scrolable | https://client.procmart.com | UI/UX issues | Pending
2025-07-02 | Product Page | In all the product pages need to add a seperator line between major content section | https://client.procmart.com/shop-by-category/6 | UI/UX issues | Closed
2025-07-03 | Privacy policy/ Terms & Conditions | Should be redirected to this pages https://www.procmart.com/privacy-policy https://www.procmart.com/terms-of-use |  | Content Issue | Closed
2025-07-03 | Support Portal | Instead of Support portal it should be Support Email: clientsuccess@procmart.com |  | Content Issue | Closed
2025-07-03 | Breadcrumbs | When a user hovers over the Hand Tools category and clicks on Ring under the Spanner subcategory, they are taken to the product listing page filtered by Spanner > Ring. In the page it shows Search Results for Spanner but it should show content as SEARCH RESULTS FOR SPANNER RING | https://client.procmart.com/search-by-product/NUT?category_id=7&category_name=FASTENERS&variants=LOCK | Display Info | Discussion Required
2025-07-03 | Shop by brand Page | In the Shop by brand section, the brand card stroke color differs from figma | https://client.procmart.com/shop-by-brand | UI/UX issues | Closed
2025-07-03 | Shop by brand container | The brand logo should be slightly larger to enhance visibility and also the card background color should be updated to a lighter shade of grey, as per the Figma reference | https://client.procmart.com | UI/UX issues | Closed
2025-07-03 | Add to cart page | After clicking "Add to Cart", the CTA correctly changes to "Added", but clicking it again incorrectly behaves like a quantity selector. | https://client.procmart.com/products/311430 |  | Closed | isnt it confusing to keep quantity input and added btn both visible at a time. can we implement simliar to other ecommerce
2025-07-03 | Legrand Brand Lisitng Page | In the Frequently Bought Together horizontal cards, the product title is overflowing the container and should be truncated. The tags are overlapping with the product image, and the card background should be updated to white as per the design. | https://client.procmart.com/shop-by-brand-name/2617?categoryId=6&brandName=Legrand&categoryName=Electrical |  | Closed
2025-07-03 | Shop by brand | In the Hydraulics & Pneumatics section under Shop by Brand, the container displays the Legrand logo, but clicking it redirects to Zoloto products. The logo and redirection link need to be corrected to ensure they point to the same brand. | https://client.procmart.com |  |  | data issue
2025-07-03 | Search | When the search dropdown appears, the rest of the page should dim with a black background and opacity to focus user attention. Currently, users can still hover over and interact with the category section, which shouldn't be the case | https://client.procmart.com |  | Closed
2025-07-03 | Search | When typing a query like "be" for "bearing", the search suggestions appear with very dim font, making them hard to read. The font weight should be increased for better visibility and readability. | https://client.procmart.com |  | Closed
2025-07-03 | Button | Currently, when any button is pressed, the shadow/stroke appears blue, which is not aligned with our brand colors. The focus/active state should use a thicker black stroke instead of blue to match the brand guidelines. | https://client.procmart.com/shop-by-category/10 |  | Closed
2025-07-03 | Order Summary Container | In order summary Container of the add to cart page, need to increase the spacing between the sections. Use figma design as refernce | https://connect.procmart.com/cart |  | Closed
2025-07-03 | Add to cart Page | In the Item list in the add to cart page, need to remove one seperator line | https://connect.procmart.com/cart |  | Closed
2025-07-03 | Add to cart page | Continue button in the add to cart and also on address page feels like skewed. Refer to figma design for button size | https://connect.procmart.com/cart |  | Closed
2025-07-07 | Product information | Product details and photo mismatch | https://client.procmart.com/products/287541
https://client.procmart.com/search-by-product/NUT?category_id=7&category_name=FASTENERS&variants=NYLOCK
2025-07-07 |  | Difference in product count and actual products (eg ABB) | https://client.procmart.com/shop-by-brand-name/1024?brandName=Abb
2025-07-07 | PDP | Breadcrumb to be added on Product detailed page | https://connect.procmart.com/products/439630 |  |  | input pending
2025-07-07 | Remove keyword 'Select' |  | https://connect.procmart.com/search-by-product/NUT?category_id=7&category_name=Fasteners
| Cart | When I am clicking on add to card and simultaneously on added the product is getting twice | https://connect.procmart.com/products/286968 | Bug

## Checklist
Checklist | Description | Succes ratio | Assign to | Comment/ Next Step | Status | Date
Picture Accuracy | Is the product image present, relevant, and correct? | ~80% | Kalyan Penumudi | Manual Effort: Codification team to allocate resources to check accuracy brand wise and upload correct images 1240 Product Image to be uploaded
Search Result Relevance | Does the product show up on relevant keyword searches? | 65% | Kalyan Penumudi Aditya Shrivastava Sanjana Kapoor | eg: Cable & Motor
Product Count Accuracy | Does the count of displayed products match the expected result set? | 99.1% | Kalyan Penumudi | Mismatch - 799 (Taparia)
Category Match | Is the product listed under the correct category/subcategory? | Tech - Cargill Custom Category Required Business - Re-effort Required | Sanjana Kapoor Vinay Arora Nirmit Sachdeva | Category Structure to be revised
Data Consistency Check | Are the uploaded Excel specs matching what's shown on the site? | 95% | Sanjana Kapoor Kalyan Penumudi | Data Reflection on portal
Specification Accuracy | Are technical specs (e.g., dimensions, material) accurate and relevant? | ~50% | Kalyan Penumudi | Tech to share count of products alreadt codified. Tech to create remaining material codes as per structure
Image Quality Standards | Are the images adhering to minimum resolution, background, and format? | ~80% | Dhiraj Gogoi

## Search accuracy Testing(KalyanS
Search Term | Expected Product(s) | Result Image | Issue Found | Comments | Assigned To | Status
6203ZZ Deep Groove Ball Bearing | 6203ZZ Deep Groove Ball Bearing |  | Wrong category shown
Taparia - Taparia SA46 Steel 1/4 Square Drive Socket Set | Socket Sets Taparia 46 Pcs 1/4 inch Square Drive Socket Set, SA46 | Yes
MCB 32amp 2Pole | Schneider Electric Acti-9 32a 2 Pole C60h-dc Mcb, A9n61535 | Yes
MCB 25amp 2Pole | Schneider Electric Acti-9 25a 2 Pole C60h-dc Mcb, A9n61533 | Yes
Sunsheet A4 protector sheet | Protector Sheet Sun Sheet Protector A4 Size Thick Make-sun - 200 | Yes
MCB 4Pole 16amp Make: Schneider | Schneider Electric Acti-9 16a 4 Pole D Curve Mcb, A9n4p16d | Yes
Allen Keys Extra Long Ball Point Set-Model number- KBHM9X | Taparia 9 Pcs Extra Long Ball Point Allen Keys Set, Kbhm 9x | Yes
Taparia - Socket Set Socket Set SA46 | Taparia 46 Pcs 1/4 Inch Square Drive Socket Set, Sa46 | Yes
VDE Pliers Set Taparia | Taparia 2 Pcs Vde Pliers Set, Svde 02 | Yes | Under Generic
KM9V, Taparia 9 Pcs Black Finish Allen Key Set in Box Packing, KM-9V | Taparia 9 Pcs Black Finish Allen Key Set In Box Packing, Km-9v | Yes
GH1000, Taparia 1000g Club Hammer with Handle, GH 1000 | Taparia 1000g Club Hammer With Handle, Gh 1000 | Yes
WIRE 120 SQ MM HOLE SIZE 12.7 MM PART NO HAS 230 | Hex 120mm2 12.7mm Aluminium End Lugs, Has-230 | Yes
Motor |  |  | Incorrect
Cable |  |  | Incorrect
MTA | bearing |  | Incorrect
APEX CLEAR TAPE 24 MMX 50 MTRS | Tape Apex Clear Tape 24 Mmx 50 Mtrs Make-apex/equivalent